## Help and Notes
Project Name: | describe your project (location, project type etc. so your designer/builder know which project this refers to)
Completion Checklist
2023-05-12
Reference Number | Action | Owner | Due Date | Status | Comment
A reference number makes it easier talk about each action | What needs to be done at completion? | Who is responsible? | When will they do it by? | Use the drop down to mark whether the task has been started or is completed | Add any other updates or comments here

## Completion Checklist
Project Name: | describe your project (location, project type etc. so your designer/builder know which project this refers to)
Completion Checklist
2023-05-12
Reference Number | Action | Action Owner | Due Date | Status | Comment
1 | Works completed | Contractor |  | Not Started
2 | Any temporary works/materials removed | Contractor |  | Not Started
3 | Final clean | Contractor |  | Not Started
4 | Works inspected and any snags/issues agreed | Client/Project Manager |  | Not Started
5 | Plan for coming back to finish anything agreed | Contractor/Client |  | Not Started
6 | Tested to make sure all plumbing works | Contractor |  | Not Started
7 | Tested to make sure all electrical items works | Contractor |  | Not Started
8 | Gas Safety Certificate | Contractor |  | Not Started
9 | Electrical Safety Certificate | Client |  | Not Started
10 | All planning conditions discharged | Client |  | Not Started
11 | Building Control Compliance Certificate | Contractor |  | Not Started
12 | Health & Safety File completed | Contractor/Architect |  | Not Started
13 | Drawings/Documents recording the design of what has been built and what has been installed | Contractor/Architect |  | Not Started
14 | Warranties and certificates (for any new products) | Contractor |  | Not Started
15 | Manuals (for any new products) | Contractor |  | Not Started
16 | Keys and pass codes handed over | Contractor |  | Not Started
17 | Meter Readings (Electric, Water, Gas) | Contractor/Client |  | Not Started
18 | Spare Parts | Contractor |  | Not Started
19
20